## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Login | 21 |  | Completed
HTML |  | Toni |  | 8 | 4 | 0 | 0 | 0 | 0 | 0.5
PHP |  | Alessio |  | 13 | 7 | 3 | 1 | 1 | 0 | 0.5
CSS |  | Emidio |  | 15 | 4 | 0 | 0 | 0 | 2 | 0
Database |  | Toni |  | 10 | 8 | 2 | 0 | 0 | 0 | 0.5
Home Pages | 21 |  | Completed
Home Page SA |  | Alessio |  | 8 | 3 | 3 | 0 | 3 | 0 | 0.5
Home Page PL |  | Veronica |  | 8 | 3 | 4 | 1 | 1 | 0 | 0.5
Home Page RM |  | Toni |  | 8 | 2 | 5 | 0 | 1 | 4 | 0.5
Home linker Module |  | Alessio |  | 5 | 3 | 0 | 0 | 0 | 0 | 0
User-friendly design Home pages | 21 |  | Completed
Bootstrap SA |  | Emidio |  | 4 | 6 | 0 | 0 | 1 | 0 | 1
Bootstrap PL |  | Emidio |  | 4 | 3 | 1 | 0 | 0 | 5 | 0
Bootstrap RM |  | Toni |  | 4 | 2 | 0.5 | 0.5 | 0 | 0 | 1
User Story #1: SA manage users | 8 |  | Completed
Create section where create and manaage users |  | Alessio |  | 5 | 1 | 2 | 0 | 0 | 3 | 1
Section profile to manage information about user |  | Alessio |  | 6 | 3 | 3 | 1 | 2 | 0 | 0
CSS Form registration |  | Emidio |  | 4 | 2 | 3 | 0 | 0 | 2 | 1
CSS Sections |  | Emidio |  | 2 | 0.5 | 0.5 | 2 | 0 | 1 | 1
User Story #2: PL view infos about activities | 21 |  | Completed
Create table where you can select activities |  | Veronica |  | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
Create section where choose weeks |  | Veronica |  | 1 | 0.5 | 0.5 | 0 | 0 | 1 | 0
Create section in which you could see infos |  | Toni |  | 9 | 4 | 3 | 0 | 1 | 5 | 0.5
Create function to download a file containing all available maintainers |  | Emidio |  | 4 | 3 | 2 | 0 | 0 | 0 | 0
Create function to download SMP file |  | Emidio |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
User Story #3: RM view and manage sites and available materials | 21 |  | Completed
Section to manage sites |  | Emidio |  | 5 | 3 | 1 | 3 | 1 | 0 | 0
Section to manage materials |  | Veronica |  | 5 | 5 | 4 | 3 | 1 | 2 | 5
DB computing |  | Alessio |  | 2 | 4 | 1 | 0.5 | 0.5 | 0 | 3
Design user frinedly |  | Emidio |  | 3 | 1 | 1 | 1 | 0 | 0 | 1
TOTAL |  |  |  | 138 | 73.5 | 41 | 14.5 | 13.5 | 25.5 | 18.5